## Sheet1
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a user, I should be able to buy shares. | PO | 8 | 6 | Not yet started | Users are able to purchase shares and have a record of them in their account
2 | As a user, I should be able to sell the shares I own. | PO | - | - | Not yet started | Users are able to sell shares they have and have the correct amount of money added to their account
3 | As a user, I want to be able to chec k my transaction history for all the stocks I have bought and sold. | PO | - | - | Not yet started | Users are able to accesstheir entire transaction history
4 | As a user I should be able to change my account information, including password and email. | PO | - | - | Not yet started | Users are able to change their account information and then be able to log in with the new details
5 | As a user, I should be able to monior a particular set of company's shares. | PO | - | - | Not yet started | Users are able choose certain companies stock to track
6 | As a user, I should be able to see where I am positioned on the leaderboard, as well as see who is currently leading. | PO | - | - | Not yet started | Users are able to see their own position on the leaderboard and the current leader
7 | As a user, I should be able to see the shares that I currently own and my financial position. | PO | 4 | 8 | Not yet started | Users are able to see all the stocks they currently own and how much money is in their account
8 | As a user, I should be able to search all the company's stocks that are registered on the ASX. | PO | - | - | Not yet started | Users are able to search the companies on ASX and get correct results back
9 | As a user, I should be able to access FAQ regarding common queries with the game. | PO | - | - | Not yet started | Users are able to access the FAQ page and see the content on it
10 | As a user, I should be able to access a general overview of my current game information. | PO | - | - | Not yet started | Users are able to access general information about their currrent game
11 | As a user, I should be able to create an account | PO | 8 | 4 | Not yet started | Users are able to create an account and then can log in with those details
12 | As a user, I should be able to open a trading account | PO | - | - | Not yet started | Users are able to create a trading account after they are logged in
13 | As a user, I should be able to see a graph with share prices plotted on it | PO |  |  | Not yet started | Users are able to see the graph plotted with share prices
14 | As an admin, I want to log into an admin page so that I can access my administration tools/maintain the game | PO | - | - | Not yet started | Admins are able to log in with their account details
15 | As an admin, I want to ban users so that I can maintain the intergrity of the servers, banning bots and people who chea | PO | - | - | Not yet started | Admins can see/search through users and ban them
16 | As an Admin, I want to shutdown the server so that I can perform server maintenance | PO | - | - | Not yet started | Admins are able to perform server shutdown and restarts
17 | As an admin, I want to access the support page so that I can review and reply to reports | PO | - | - | Not yet started | Admins are able to access the support page and see reports
18 | As an admin, I want to comment on support tickets so that I can address a report a user has posted | PO | - | - | Not yet started | Admins are able to comment/reply to reports
19 | As an admin, I want to update support tickets status to "closed, pending and unread" so that I can show the user the status of their ticket | PO | - | - | Not yet started | Admins are able to chance the status of reports
20 | As an admin, I want to promote a user to an admin so that I can allocate the role of an admin to a user | PO | - | - | Not yet started | Admins are able to give normal users admin rights
21 | As an admin, I want to backup the server so that I can restore the server when needed to | PO | - | - | Not yet started | Admins are able to backup and mantain servers
22 | As an admin, I want to be able to access overall statitstics(user log ins everyday, how active are users when they are logged in, etc) so that I can document the games life | PO | - | - | Not yet started | Admins are able to accesss the statistics page and view the statistics in it
23 |  | PO | - | - | Not yet started
24 |  | PO | - | - | Not yet started
25 |  | PO | - | - | Not yet started
26 |  | PO | - | - | Not yet started
27 |  | PO | - | - | Not yet started
28 |  | PO | - | - | Not yet started
29 |  | PO | - | - | Not yet started
30 |  | PO | - | - | Not yet started
31 |  | PO | - | - | Not yet started
32 |  | PO | - | - | Not yet started
33 |  | PO | - | - | Not yet started
34 |  | PO | - | - | Not yet started
35 |  | PO | - | - | Not yet started
36 |  | PO | - | - | Not yet started
37 |  | PO | - | - | Not yet started
38 |  | PO | - | - | Not yet started
39 | The system should be responsive for both tablet and mobile resolutions. | PO | - | - | Not yet started